## Workplan
UNIVERSITY OF SANTO TOMAS — Electronics Engineering Department
An Evaluation of Multi-Agent Reinforcement Learning for Dynamic Bus Scheduling Under Non-Ideal Conditions
Group B3 · Workplan · Reporting time: Mid-Stage Assessment 1 / Progress Report 1 (Week 5, Sept 7–12, 2026)
LEGEND: | Accomplished | Original plan | Start: Aug 10, 2026 ¦ ◀ Reporting line at end of W5 — MSA 1 (Sep 7–12): scope shown = through SUMO calibration (EO 1.1). MSA 2 — Oct 5–10 (W9) ¦ MSA 3 — Nov 23–28 (W16) ¦ Research Paper & Poster — Nov 30–Dec 5 (W17). Weather regime is synthetic; NOAA join is a stretch item.
| Catch-up | Milestone / MSA
Specific Objective | Expected Output | Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
|  |  | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 ★MSA 1 | Sep 14 | Sep 21 | Sep 28 | Oct 5 ★MSA 2 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 ★MSA 3 | Nov 30 ★Paper | Dec 7
SO 1 — Environment Construction (construct a stochastic traffic simulation environment) | EO 1.1 — A validated simulation model of a defined operational scope (empirical calibration) | Acquire CapMetro APC dataset; select Route 801, direction 6; document exclusions | bar: W1
Clean & filter raw APC → 229,421-event subset (six rules) + SHA-256 provenance | bar: W2
Reduce per-stop demand, dwell, running time & distance → stops.csv | bar: W2 to W3
Build the 26-stop corridor network in SUMO | bar: W3 to W4
Calibrate edge speeds to empirical travel times (GEH < 5, RMSPE 0.75%); validation figure | bar: W4 to W5
| EO 1.2 — An environment simulator with adjustable parameters for non-ideal conditions | Implement demand-responsive dwell (Newell–Potts bunching coupling) | bar: W6
Build disturbance generators: demand, surge, traffic, weather, breakdown (D/S/T/W/B) | bar: W6 to W7
Pre-draw per-seed disturbance fields for paired (matched-seed) comparison | bar: W7 to W8
Parameterize the synthetic lognormal weather regime (labeled synthetic) | bar: W8 to W9
SO 2 — Algorithm Implementation (develop and implement a MARL approach) | EO 2.1 — A formulated agent architecture (discrete state & action; continuous reward) | Derive the 5 control stops from the four §3.2.2 criteria | bar: W7
Define the 7-vector observation and the 10-action (hold × skip) space | bar: W8
Build the reward-term library (irregularity, waiting, skip penalties) | bar: W9
Implement parameter-shared Double-DQN (CTDE; semi-MDP transition assembly) | bar: W9 to W10
Build the config-driven training/eval harness + fail-fast reward gate | bar: W10 to W11
Reward-coefficient tuning study (EO 2.1 coefficients) | bar: W11
Full domain-randomized training run | bar: W11 to W12
SO 3 — Performance Evaluation (under ideal and non-ideal conditions) | EO 3.1 — Statistical assessment under IDEAL conditions vs baselines | Implement baselines: No-Control, Forward-Headway, Even-Headway | bar: W10
N = 30 matched-seed Monte-Carlo, Stage A (D+T); bootstrap 95% CIs | bar: W11 to W12
Evaluate the trained policy as a fourth controller (ideal) | bar: W13 to W14
Tabulate waiting time / travel time / headway-CV against baselines | bar: W14
| EO 3.2 — Statistical assessment under NON-IDEAL conditions (degradation) | Run the activation matrix: ablations S/W/B and combined Stage B | bar: W13 to W14
Report degradation relative to ideal, with significance | bar: W15
Produce the degradation curve and Marey (time–space) diagrams | bar: W15
Empirical NOAA precipitation join — weather validation (stretch / future) | bar: W16
Prepared for MSA 1 (Progress Report 1). Milestone pacing: MSA 1 (W5) → environment calibrated (EO 1.1); MSA 2 (W9) → non-ideal simulator + MARL formulation (EO 1.2, EO 2.1); MSA 3 (W16) → full training + evaluation results (EO 3.1, EO 3.2). Green = accomplished as of the reporting line; blue = original plan; orange = catch-up.